## charter
General Project Information
Project Name | Skill Gap Assessment
Project Champion | Mr. Nitin Shah
Project Sponsor | Prazo Solutions
Project Manager | Mr. Nitin Shah
Stakeholders | Prazo Solutions
Expected Start Date | 2018-02-05
Expected Completion Date* | 2018-06-05
Project Details
Mission | To build an application to do end to end skill management for the organization.
Vision | To provide a brief overview of Skill Gap Assessment to promote a shared understanding of it before a more detailed plan.
Scope | The main scope of “Skill Gap Assessment” is to manage employee’s skill in an organization. The system has an admin login who can add question or a set of questions for a particular skill. Each skill can be categorize into different sub categories. Each skill can have multiple questions. Each question may have a single answer or a multiple answer. Admin can assign rating (in simple term marks) for each question and each group of questions. Further there will be a manager login in which he can assess employee on a particular skill. Manager can also approve the assessment done by the employee. Further there will be an employee login who can assess himself on a particular questionnaire.
Date: | 2018-06-05

## project_plan
Project Name | Skill Gap Assessment
Project Manager | Mr. Nitin Shah
Project Deliverable | Yes
Scope Statement | Refer Introduction Section
Start Date | 2018-02-05
End Date* | 2018-06-05
Task Name | Responsible | Start Date | End Date | Days | Status
Sprint 1 | Abhinav Shah | 2018-02-15 | 2018-02-25 | 10 | Completed
Login | Abhinav Shah | 2018-02-15 | 2018-02-25 | 10 | Completed
Sprint 2 | Abhinav Shah | 2018-02-28 | 2018-03-16 | 16 | Completed
Manage Category | Abhinav Shah | 2018-02-28 | 2018-03-04 | 5 | Completed
Manage Sub Category | Abhinav Shah | 2018-03-05 | 2018-03-09 | 5 | Completed
Manage Skill | Abhinav Shah | 2018-03-10 | 2018-03-16 | 6 | Completed
Sprint 3 | Abhinav Shah | 2018-03-18 | 2018-03-30 | 12 | Completed
Add Form | Abhinav Shah | 2018-03-18 | 2018-03-25 | 7 | Completed
View/Update Form | Abhinav Shah | 2018-03-26 | 2018-03-30 | 4 | Completed
Sprint 4 | Abhinav Shah | 2018-04-02 | 2018-04-12 | 10 | Completed
Add Question | Abhinav Shah | 2018-04-02 | 2018-04-04 | 3 | Completed
View Question | Abhinav Shah | 2018-04-05 | 2018-04-08 | 4 | Completed
Update Question | Abhinav Shah | 2018-04-09 | 2018-04-12 | 3 | Completed
Sprint 5 | Abhinav Shah | 2018-04-14 | 2018-04-24 | 10 | Pending
Manager Assessment | Abhinav Shah | 2018-04-14 | 2018-04-20 | 6 | Pending
Approve Employee Assessment | Abhinav Shah | 2018-04-21 | 2018-04-24 | 4 | Pending
Sprint 6 | Abhinav Shah | 2018-04-26 | 2018-05-05 | 10 | Not Started
Employee Add Assessment | Abhinav Shah | 2018-04-26 | 2018-04-30 | 5 | Not Started
View Assessment | Abhinav Shah | 2018-05-01 | 2018-05-05 | 5 | Not Started
Sprint 7 | Abhinav Shah | 2018-05-08 | 2018-05-15 | 8 | Not Started
Customer Assessment | Abhinav Shah | 2018-05-08 | 2018-05-15 | 8 | Not Started
Sprint 8 | Abhinav Shah | 2018-05-18 | 2018-05-28 | 10 | Not Started
Admin View Response | Abhinav Shah | 2018-05-18 | 2018-05-23 | 6 | Not Started
Generate Report | Abhinav Shah | 2018-05-24 | 2018-05-28 | 4 | Not Started
Sprint 9 | Abhinav Shah | 2018-05-29 | 2018-06-05 | 8 | Not Started
Manage Dashboard | Abhinav Shah | 2018-05-29 | 2018-06-05 | 8 | Not Started

## user_story
User Story ID | As a <type of user> | I want to <perform some task> | So that I can <achieve some goal> | Priority
1 | Admin | Enter email and password | Admin logs into the system. | High
2 | Admin | Adds category | All the classes are added. | Medium
3 | Admin | Adds sub category | All the sub category are added for each category. | Medium
4 | Admin | Adds skill | All the skill are added for each sub category. | Medium
5 | Admin | Add form | Form is created for each specific skill | High
6 | Admin | Add question | Questions are added for a specific form | High
7 | Admin | Manage dashboard | Admin manages dashboard | High
8 | Admin | View responses | Admin views responses | Medium
9 | Manager | Approve assessment | Manager approves employee’s assessment | High
10 | Manager | Update employee assessment | Manager can update employee’s assessment | Medium
11 | Manager | Assess employee | Manager can assess employee | medium
12 | Employee | Self-assessment | Employee can assess himself | Medium
13 | Employee | View response | Employee can view his response | low
14 | Customer | Asses project team | Customer can assess project team | medium

## release_plan
Sprint | Task | Start | End | Days | Status | Release Date | Goal
1 | Login | 2018-02-15 | 2018-02-25 | 10 | Released | 2018-02-26 | Create Login Module
2 | Manage Category | 2018-02-28 | 2018-03-04 | 5 | Released | 2018-03-04 | Manage Category Details
| Manage Sub Category | 2018-03-05 | 2018-03-09 | 5 | Released | 2018-03-09 | Manage Sub Category Details
| Manage Skill | 2018-03-10 | 2018-03-16 | 6 | Released | 2018-03-17 | Manage Skill Details
3 | Add Form | 2018-03-18 | 2018-03-25 | 7 | Released | 2018-03-25 | Add Form Details
| View/Update Form | 2018-03-26 | 2018-03-30 | 4 | Released | 2018-04-01 | View/Update Form Details
4 | Add Question | 2018-04-02 | 2018-04-04 | 3 | Released | 2018-04-04 | Add Question Detail
| View Question | 2018-04-05 | 2018-04-08 | 4 | Released | 2018-04-08 | View Questions
| Update Question | 2018-04-09 | 2018-04-12 | 3 | Released | 2018-04-13 | Update Question Details
5 | Manager Assessment | 2018-04-14 | 2018-04-20 | 6 | Not Released | 2018-04-20 | Manager Assess Employee
| Approve Employee Assessment | 2018-04-21 | 2018-04-24 | 4 | Not Released | 2018-04-25 | Manager Approve Employee Assessment
6 | Employee Add Assessment | 2018-04-26 | 2018-04-30 | 5 | Not Released | 2018-04-30 | Employee Assessment
| View Assessment | 2018-05-01 | 2018-05-05 | 5 | Not Released | 2018-05-05 | Employee Can View His Assessment
7 | Customer Assessment | 2018-05-08 | 2018-05-15 | 8 | Not Released | 2018-05-15 | Customer Can Assess Team
8 | Admin View Response | 2018-05-18 | 2018-05-23 | 6 | Not Released | 2018-05-23 | Admin Can View All Response
| Generate Report | 2018-05-24 | 2018-05-28 | 4 | Not Released | 2018-05-28 | Admin Can Generate Report
9 | Manage Dashboard | 2018-05-29 | 2018-06-05 | 8 | Not Released | 2018-06-05 | Admin Can Manage Dashboard

## backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | Yes | Yes | High | Complete | 8 | Yes
Login | Yes | Yes | High | Complete | 8 | Yes
Sprint 2 | Yes | Yes | Medium | Complete | 24 | Yes
Manage Category | Yes | Yes | Medium | Complete | 8 | Yes
Manage Sub Category | Yes | Yes | Medium | Complete | 8 | Yes
Manage Skill | Yes | Yes | Medium | Complete | 8 | Yes
Sprint 3 | Yes | Yes | High | Complete | 32 | Yes
Add Form | Yes | Yes | High | Complete | 16 | Yes
View/Update Form | Yes | Yes | High | Complete | 16 | Yes
Sprint 4 | Yes | Yes | High | Complete | 48 | Yes
Add Question | Yes | Yes | High | Complete | 16 | Yes
View Question | Yes | Yes | High | Complete | 16 | Yes
Update Question | Yes | Yes | High | Complete | 16 | Yes
Sprint 5 | Yes | Yes | High | Pending | 16 | Yes
Manager Assessment | Yes | Yes | Medium | Pending | 8 | Yes
Approve Employee Assessment | Yes | Yes | High | Pending | 8 | Yes
Sprint 6 | Yes | Yes | High | Not Started | 8 | Yes
Employee Add Assessment | Yes | Yes | Medium | Not Started | 4 | Yes
View Assessment | Yes | Yes | Low | Not Started | 4 | Yes
Sprint 7 | Yes | Yes | High | Not Started | 4 | Yes
Customer Assessment | Yes | Yes | Medium | Not Started | 4 | Yes
Sprint 8 | Yes | Yes | High | Not Started | 20 | Yes
Admin View Response | Yes | Yes | Low | Not Started | 4 | Yes
Generate Report | Yes | Yes | High | Not Started | 16 | Yes
Sprint 9 | Yes | Yes | High | Not Started | 20 | Yes
Manage Dashboard | Yes | Yes | High | Not Started | 20 | Yes

## test_Plan
Project Name: Skill Gap Assessment
Test Case ID: T1 | Test Designed by: Abhinav Shah
Test Priority (Low/Medium/High): Med | Test Designed date: 04/03/2018
Module Name: Admin Add Category | Test Executed by: Abhinav Shah
Test Title: Add Category Details | Test Execution date: 04/03/2018
Description: Admin Adds The Category
Pre-conditions: Admin Should Be Logged In
Dependencies:
Step | Test Steps | Test Data | Expected Result | Actual Result | Status
1 | Navigate To Add Category Page | Click On Add | Allow | Pass | Pass
2 | Enter Category Details | Add Category Details | Allow | Pass | Pass
3 | Add Button | Click On Add Button | Allow | Pass | Pass
Project Name: Skill Gap Assessment
Test Case ID: T2 | Test Designed by: Abhinav Shah
Test Priority (Low/Medium/High): Med | Test Designed date: 09/03/2018
Module Name: Admin Add Sub Category | Test Executed by: Abhinav Shah
Test Title: Add Sub Category Details | Test Execution date: 09/03/2018
Description: Admin Adds The Sub Category
Pre-conditions: Admin Should Be Logged In
Dependencies:
Step | Test Steps | Test Data | Expected Result | Actual Result | Status
1 | Navigate To Add Sub Category Page | Click On Add | Allow | Pass | Pass
2 | Enter Sub Category Details | Add Sub Category Details | Allow | Pass | Pass
3 | Add Button | Click On Add Button | Allow | Pass | Pass
Project Name: Skill Gap Assessment
Test Case ID: T3 | Test Designed by: Abhinav Shah
Test Priority (Low/Medium/High): Med | Test Designed date: 16/03/2018
Module Name: Admin Add Skill | Test Executed by: Abhinav Shah
Test Title: Add Skill Details | Test Execution date: 16/03/2018
Description: Admin Adds The Skill
Pre-conditions: Admin Should Be Logged In
Dependencies:
Step | Test Steps | Test Data | Expected Result | Actual Result | Status
1 | Navigate To Add Skill Page | Click On Add | Allow | Pass | Pass
2 | Enter Skill Details | Add Skill Details | Allow | Pass | Pass
3 | Add Button | Click On Add Button | Allow | Pass | Pass