## Sheet1
Task Name | Responsible | Start Date | End Date | Days | Status
Sprint 1 | Abhinav Shah | 2018-02-15 | 2018-02-25 | 10 | Completed
Login | Abhinav Shah | 2018-02-15 | 2018-02-25 | 10 | Completed
Sprint 2 | Abhinav Shah | 2018-02-28 | 2018-03-16 | 16 | Completed
Manage Category | Abhinav Shah | 2018-02-28 | 2018-03-04 | 5 | Completed
Manage Sub Category | Abhinav Shah | 2018-03-05 | 2018-03-09 | 5 | Completed
Manage Skill | Abhinav Shah | 2018-03-10 | 2018-03-16 | 6 | Completed
Sprint 3 | Abhinav Shah | 2018-03-18 | 2018-03-30 | 12 | Completed
Add Form | Abhinav Shah | 2018-03-18 | 2018-03-25 | 7 | Completed
View/Update Form | Abhinav Shah | 2018-03-26 | 2018-03-30 | 4 | Completed
Sprint 4 | Abhinav Shah | 2018-04-02 | 2018-04-12 | 10 | Completed
Add Question | Abhinav Shah | 2018-04-02 | 2018-04-04 | 3 | Completed
View Question | Abhinav Shah | 2018-04-05 | 2018-04-08 | 4 | Completed
Update Question | Abhinav Shah | 2018-04-09 | 2018-04-12 | 3 | Completed
Sprint 5 | Abhinav Shah | 2018-04-14 | 2018-04-24 | 10 | Pending
Manager Assessment | Abhinav Shah | 2018-04-14 | 2018-04-20 | 6 | Pending
Approve Employee Assessment | Abhinav Shah | 2018-04-21 | 2018-04-24 | 4 | Pending
Sprint 6 | Abhinav Shah | 2018-04-26 | 2018-05-05 | 10 | Not Started
Employee Add Assessment | Abhinav Shah | 2018-04-26 | 2018-04-30 | 5 | Not Started
View Assessment | Abhinav Shah | 2018-05-01 | 2018-05-05 | 5 | Not Started
Sprint 7 | Abhinav Shah | 2018-05-08 | 2018-05-15 | 8 | Not Started
Customer Assessment | Abhinav Shah | 2018-05-08 | 2018-05-15 | 8 | Not Started
Sprint 8 | Abhinav Shah | 2018-05-18 | 2018-05-28 | 10 | Not Started
Admin View Response | Abhinav Shah | 2018-05-18 | 2018-05-23 | 6 | Not Started
Generate Report | Abhinav Shah | 2018-05-24 | 2018-05-28 | 4 | Not Started
Sprint 9 | Abhinav Shah | 2018-05-28 | 2018-06-05 | 9 | Not Started
Manage Dashboard | Abhinav Shah | 2018-05-28 | 2018-06-05 | 9 | Not Started
User Story ID | As a <type of user> | I want to <perform some task> | So that I can <achieve some goal> | Priority
1 | Admin | Enter email and password | Admin logs into the system. | High
2 | Admin | Adds category | All the classes are added. | Medium
3 | Admin | Adds sub category | All the sub category are added for each category. | Medium
4 | Admin | Adds skill | All the skill are added for each sub category. | Medium
5 | Admin | Add form | Form is created for each specific skill | High
6 | Admin | Add question | Questions are added for a specific form | High
7 | Admin | Manage Dashboard | Admin manages dashboard | High
8 | Admin | View Reponses | Admin views responses | Medium
9 | Manager | Approve assessment | Manager approves employee’s assessment | High
10 | Manager | Update employee assessment | Manager can update employee’s assessment | Medium
11 | Manager | Assess employee | Manager can assess employee | medium
12 | Employee | Self-assessment | Employee can assess himself | Medium
13 | Employee | View response | Employee can view his response | low
14 | Customer | Asses project team | Customer can assess project team | medium